## Document Control
© 2023 Adobe Inc. All rights reserved. Adobe Confidential – Not for External Distribution.
Project Review Summary - Adobe Analytics
Document Title | Project Review Summary - Adobe Analytics
Consultant(s)
Reviewer | Gergana Stoyanova
Document Purpose | A review check-list to ensure all required documentation is up-to-date for the project and recommended settings for AA with Edge SDK are enabled
Version Number | Date | Author | Comments
v1.0 | 2023-09-22 | Sandipan Roy | Initial release
Client Name | TCB
Go-Live Date | 2023-09-30
Report Suites | techcombank-vn-dev, techcombank-vn-prod

## Pre Go-Live Checklist
Pre/Post Go-Live | Item | What to check? | Status (color coding) | Date Reviewed | Follow-up Notes/Comments
Pre Go-Live | Data Layer | Ensure latest data layer from lower envrionement are present in Production | 0 |  | Need to check this in Final Test Flight build
Pre Go-Live | Schema | Ensure experience event schema is created with required field groups | 1 | 2023-09-22
Pre Go-Live | Schema | Ensure that the XDM schema in AEP is identical in both the sandboxes (Dev & Prod) | 1 | 2023-09-22
Pre Go-Live | Schema | Ensure dataset and schema are enabled for profile as needed. And adding ECID as a separate variable for the scope of CJA | 0 | 2023-09-25 | Dataset and schema are available in prod environment but are not enabled for profile because - AA data is planned to be released in Nov'23 post CAB approval.
Pre Go-Live | Dataset | Ensure dataset is created or migrated to Staging/Production as needed for reporting needs. | 1 |  | AEP service added to datastreams but not enabled because AA data is planned to be released in Nov'23 post CAB approval.
Pre Go-Live | Datastream | Is the datastream created on the correct sandbox? | 1 | 2023-09-22
Pre Go-Live | Datastream | Are all the required services added to the datastream? Eg: Reportsuite ID for AA, dataset name for AEP, Property details for target, Launch Property for Event Forwarding etc | 0 | 2023-09-22 | AEP service added to datastreams but not enabled because AA data is planned to be released in Nov'23 post CAB approval.
Pre Go-Live | Datastream | Ensure all mapping created has been copied over correctly. | 1 | 2023-09-22
Pre Go-Live | Adobe Launch - Installation | Right version of the Launch Snippet (production) added in all pages of production site | 0 |  | Need to check this in Final Test build
Pre Go-Live | WebSDK Extension | Ensure correct CNAME is updated for Edge domain | Not Applicable
Pre Go-Live | WebSDK Extension | Ensure that ECID migration is enabled. | Not Applicable
Pre Go-Live | Mobile Edge SDK Extension | Ensure datastream is selected correctly for respective environments | 0 |  | Need to point to prod sandbox and datastream, before Go live.
Pre Go-Live | Mobile Edge SDK Extension | Ensure privacy setting are configured as required (Consent preferences) | 1
Pre Go-Live | Adobe Launch - Extensions | All extensions should be published (this should copy all the configuration variable settings, validated from dev) | 0 |  | Need to push it before Go live
Pre Go-Live | Adobe Launch - Data Elements | All data elements should be published | Not Applicable
Pre Go-Live | Adobe Launch-Data Elements | Ensure the XDM Object Data Element has Sandbox pointing to Production | Not Applicable
Pre Go-Live | Adobe Launch - Rules | All rules should be published. Make a note of disabled rules during testing phase | 0 |  | To be done on Sep 30
Pre Go-Live | Adobe Launch-Publish | ensure a Hit is sent to test out the production is recieving data from the production datastream by pointing the dev sandbox to production. | Not Applicable
Pre Go-Live | Launch Library | Ensure Library is published in the right environment (dev/staging/prod) | 0 |  | To be done on Sep 30
Pre Go-Live | Report suite - General Account Settings | Site title, Base URL, Time Zone, default Page, Multi-byte Character Support (incase of multi-lingual global report suites) | 1 | 2023-09-22
Pre Go-Live | Report suite - Internal URL filters | Add website's internal domains | Not Applicable
Pre Go-Live | Report suite - Paid Search Detection | Query string parameters used for paid search | Not Applicable
Pre Go-Live | Report suite - Marketing Channels | Ensure that the marketing channel processing rules are same accross all the applicable report suites (dev & prod) | 0 |  | Waiting for TCB's final list
Pre Go-Live | Report suite - Processing Rules | All tested rules copied from dev report suite | 1 | 2023-09-22
Pre Go-Live | Report suite - Bot Rules | The bot rules used to filter out bot and spiders | 1 | 2023-09-22 | Default
Pre Go-Live | Report suite - Traffic Variables | Final list of tested props/changed names copied from Dev report suite | 1 | 2023-09-22 | No traffic variables currently used
Pre Go-Live | Report suite - Conversion Variables | Final list of tested eVars/changed names copied from Dev report suite | 1 | 2023-09-22
Pre Go-Live | Report suite - Conversion Variables: expiration & allocation | s.campaign allocation/expiration & other eVars allocation/expiration | 1 | 2023-09-22
Pre Go-Live | Report suite - Success Events | Final list of tested events/changed names copied from Dev report suite | 1 | 2023-09-22
Pre Go-Live | Report suite - Success Events: Participation | Ensure participation to be set on selected metrics | 1 | 2023-09-22
Pre Go-Live | Report suite - List Variables | Final list of tested listVars/changed names copied from Dev report suite | 1 | 2023-09-22
Pre Go-Live | Report suite - Marketing Channels | Setup marketing channels processing rules for prod report suite | 0 |  | Waiting for TCB's final list
Pre Go-Live | Report suite - TimeStamp | Ensure right timestamp setting enabled in production report suite | 1 | 2023-09-22 | Timestamp is enabled
Pre Go-Live | Report suite - Classifications | Ensure classifications file reception to the FTP location | Not Applicable
Pre Go-Live | Report suite - Classification Rules | Ensure tested rules are copied to the production report suites and activated | Not Applicable
Pre Go-Live | Data Validation | Ensure ECID is getting captured | 1 | 2023-09-22
Pre Go-Live | Data Validation | Compare Page Views and Custom Page Views to ensure no inflation is seen | 1 | 2023-09-22
Pre Go-Live | Data Validation | Ensure usecases are validated using reports | 1 | 2023-09-22
Pre Go-Live | Data Validation | Clean up any dataset errors before go live | 0 |  | Work in progress by CDP and AA team
Pre Go-Live | Data Validation | Ensure Data Validation is complete between AEP and Analytics | 0 |  | TBD
Post Go-Live | Data Validation | Ensure that the cookie consent is intact | Not Applicable |  | Not applicab;e
Pre Go-Live | Data Validation | Ensure A4T report is populating in dev report suite | 1 | 25/09/23
Pre Go-Live | Data Validation | Ensure Campaign integration is working in dev | 1 | 25/09/2023

## Document Checklist
TCB
Overall Documentation Checklist for Report Suite: techcombank-vn-dev, techcombank-vn-prod
S.No | Item | Notes/Comments | Status (color coding) | Date Reviewed
1 | BRD | Signed off and email confirmation | 1 | 2023-09-22
2 | SDR | No sign off received on SDR but was discussed internally | 1 | 2023-09-22
3 | TSD | Uploaded to TCB shaepoint | 1 | 22-092023
4 | Implementation Validation | Done | 1 | 22-092023
5 | Go-live checklist | In progress | 0 | 2023-09-22
6 | Go-Live date | 2023-09-30 | 6 | 2023-09-22
7 | Post Go-live Sanity Checks | Yet to be done | 0 | 2023-09-22
8 | Project Current Status | Go live on 30-09-2023 | 1 | 2023-09-22

## Adobe Launch Rules & Elements (hidden)
Domain | www.abcxyz.com
Library Name (production) | satelliteLib-d61369d7355755b7c1cc23efcab69b5ad4d3f020
Name | Type | Trigger | Scope | Status | Properties | Conditions | Adobe Analytics | Classic Analytics | Universal Analytics | Third Party
Article: Download Article | Event Based Rule | click | .actions-bar__download a.js-exportto | 0 |  | function(){return _satellite.setVar(&quot;A_Download_Article_socialPlatform&quot;,$(this).text()),_satellite.getVar(&quot;A_Download_Article_socialPlatform&quot;),!0} | Link Name: linkName=%PageName%: Download; Link Type: linkType=Custom Link; Event: event1=event1; Event: event12=event12; Prop: prop1=%ArticleComplianceCode%; Prop: prop16=Download; Prop: prop7=%PageTitle%;
Article: Load More Fund Clicks | Event Based Rule | click | .related-product-load-more | 0 |  |  | Link Name: linkName=Load More: Funds; Link Type: linkType=Custom Link;
Article: Load More Insights Clicks | Event Based Rule | click | .related-insights__load-more a.load-more | 0 |  |  | Link Name: linkName=Load More: Insights; Link Type: linkType=Custom Link;
Article: Print Article | Event Based Rule | click | .actions-bar__print.js-pirnt | 0 |  |  | Link Name: linkName=%PageName%: Print; Link Type: linkType=Custom Link; Event: event12=event12; Event: event3=event3; Prop: prop1=%ArticleComplianceCode%; Prop: prop16=Print; Prop: prop7=%PageTitle%; Prop: prop9=%PageTitle%;
Article: Share Article | Event Based Rule | click | .at-share-btn-elements .at-share-btn | 0 |  | function(){return _satellite.setVar(&quot;A_Share_Article_socialPlatform&quot;,$(this).find(&quot;title&quot;).text()),_satellite.getVar(&quot;A_Share_Article_socialPlatform&quot;),!0} | Link Name: linkName=%PageName%: Share to %A_Share_Article_socialPlatform%; Link Type: linkType=Custom Link; Event: event12=event12; Event: event2=event2; Prop: prop1=%ArticleComplianceCode%; Prop: prop16=Share; Prop: prop7=%PageTitle%; Prop: prop8=%A_Share_Article_socialPlatform%;
Article: View Full Bio | Event Based Rule | click | .profile-callout__profile-details a.profile-callout__profile-bio | 0 |  | function(){var e=$(this).closest(&quot;.profile-callout__profile-details&quot;).find(&quot;.profile-callout__profile-name&quot;).text();return _satellite.setVar(&quot;A_ViewFullBio_profileName&quot;,e),_satellite.getVar(&quot;A_ViewFullBio_profileName&quot;),!0} | Link Name: linkName=Bio: %A_ViewFullBio_profileName%; Link Type: linkType=Custom Link; Prop: prop10=%A_ViewFullBio_profileName%;
Change Location | Event Based Rule | click | .utility-nav .change-location .dropdown-with-bg li:not(.region) | 0 |  | function(){var e=_satellite.getVar(&quot;Location&quot;),t=$(this).data(&quot;locationkey&quot;);return _satellite.setVar(&quot;utilityNavLocationChange_data_newloc&quot;,t),_satellite.getVar(&quot;utilityNavLocationChange_data_newloc&quot;),e!=t} | Link Name: linkName=Change Location; Link Type: linkType=Custom Link; Event: event9=event9; Prop: prop13=%Location% : %utilityNavLocationChange_data_newloc%;
Change Role | Event Based Rule | click | .utility-nav .investment-professional .dropdown-with-bg li | 0 |  | function(){var e=_satellite.getVar(&quot;Role&quot;),t=$(this).text();return _satellite.setVar(&quot;UtilityNavRoleChange_data_newrole&quot;,t),_satellite.getVar(&quot;UtilityNavRoleChange_data_newrole&quot;),e!=t} | Link Name: linkName=Change Role; Link Type: linkType=Custom Link; Event: event8=event8; Prop: prop12=%Role% : %UtilityNavRoleChange_data_newrole%;
Choose from Investment Options/Product Category Selector | Event Based Rule | change | .insights-callout select.product-dropdown | 0 |  | function(){var e=$(this),t=$(&quot;option:selected&quot;,e).text();return console.log(&quot;ChooseInvestmentOption = &quot;+t),_satellite.setVar(&quot;ChooseInvestmentOption&quot;,t),_satellite.getVar(&quot;ChooseInvestmentOption&quot;),null!=t} | Link Name: linkName=Prod Category Selector: %ChooseInvestmentOption%; Link Type: linkType=Custom Link; Event: event41=event41; eVar: eVar33=%ChooseInvestmentOption%; Prop: prop33=%ChooseInvestmentOption%;
Common: Hero Click | Event Based Rule | click | .hero-banner img, .profile-banner__img img | 0 |  | function(){var e=null!=$(this).attr(&quot;src&quot;)?$(this).attr(&quot;src&quot;):$(this).attr(&quot;srcset&quot;);return console.log(&quot;Hero Clicked img: &quot;+e),_satellite.setVar(&quot;Common_HeroClick_src&quot;,e),_satellite.getVar(&quot;Common_HeroClick_src&quot;),!0} | Link Name: linkName=HeroClick: %Common_HeroClick_src%; Link Type: linkType=Custom Link;
Common: Related Insight | Event Based Rule | click | .related-insights__content .title a, .related-insights-tab__content .title a | 0 |  |  | Link Name: linkName=Related Insights: %this.@text%; Link Type: linkType=Custom Link;
Common: Sticky Nav Tab Clicks | Event Based Rule | click | .in-page-navigation .in-page-navigation__tab a | 0 |  |  | Link Name: linkName=Sticky Nav: %this.@cleanText%; Link Type: linkType=Custom Link;
Common: Subtab Category Clicks | Event Based Rule | click | .in-page-navigation__left-tab ul.tabs li | 0 |  | function(){var e=$(this).closest(&quot;.in-page-navigation__left-tab&quot;).find(&quot;.compheading.align-left-inpage&quot;).text();return _satellite.setVar(&quot;Common_SubtabCategory_tabHead&quot;,e),_satellite.getVar(&quot;Common_SubtabCategory_tabHead&quot;),!0} | Link Name: linkName=%Common_SubtabCategory_tabHead%: %this.@cleanText%; Link Type: linkType=Custom Link;
Common: Tooltip | Event Based Rule | click | .tooltip-pop | 0 |  |  | Link Name: linkName=Tooltip; Link Type: linkType=Custom Link;
Expand Login Widget | Event Based Rule | click | .login-register:not(.closed)>.login-button | 0 |  |  | Link Name: linkName=Expand Login; Link Type: linkType=Custom Link;
Global Footer: Footer Link Clicks | Event Based Rule | click | .global-footer__links .sublink-content li > a | 0 |  |  | Link Name: linkName=Footer: %this.@cleanText%; Link Type: linkType=Custom Link; eVar: eVar19=%CampaignUserId%; eVar: eVar2=%Role%; eVar: eVar23=%PageName%; eVar: eVar3=%Location%; eVar: eVar4=%Language%; eVar: eVar5=%LoginStatus%; Prop: prop15=%PageURL%; Prop: prop19=D=v19; Prop: prop2=D=v2; Prop: prop23=D=v23; Prop: prop3=D=v3; Prop: prop4=D=v4; Prop: prop5=D=v5;
Global Footer: Footer Logo Clicks | Event Based Rule | click | .global-footer__logo>a | 0 |  |  | Link Name: linkName=Footer: Global Nav Logo; Link Type: linkType=Custom Link; eVar: eVar19=%CampaignUserId%; eVar: eVar2=%Role%; eVar: eVar23=%PageName%; eVar: eVar3=%Location%; eVar: eVar4=%Language%; eVar: eVar5=%LoginStatus%; Prop: prop15=%PageURL%; Prop: prop19=D=v19; Prop: prop2=D=v2; Prop: prop23=D=v23; Prop: prop3=D=v3; Prop: prop4=D=v4; Prop: prop5=D=v5;
Global Footer: Social Exit Clicks | Event Based Rule | click | .global-footer__social-icon .social-icons | 0 |  |  | Link Name: linkName=Footer: Social Exit: %this.title%; Link Type: linkType=Custom Link; eVar: eVar19=%CampaignUserId%; eVar: eVar2=%Role%; eVar: eVar23=%PageName%; eVar: eVar3=%Location%; eVar: eVar4=%Language%; eVar: eVar5=%LoginStatus%; Prop: prop15=%PageURL%; Prop: prop19=D=v19; Prop: prop2=D=v2; Prop: prop23=D=v23; Prop: prop3=D=v3; Prop: prop4=D=v4; Prop: prop5=D=v5;
Global Header: Change Search Results View | Event Based Rule | click | .mega-nav-search__search-view a | 0 |  | function(){var e=$(this).hasClass(&quot;js-grid-icon&quot;)?&quot;Grid&quot;:&quot;List&quot;;return _satellite.setVar(&quot;GH_ChangeSearchResultsView_data_searchView&quot;,e),_satellite.getVar(&quot;GH_ChangeSearchResultsView_data_searchView&quot;),!0} | Link Name: linkName=View : %GH_ChangeSearchResultsView_data_searchView%; Link Type: linkType=Custom Link;
Global Header: Close Search | Event Based Rule | click | .js-search-close | 0 |  |  | Link Name: linkName=Search: Close; Link Type: linkType=Custom Link;
Global Header: Contact Us Clicks | Event Based Rule | click | .global-header__global-nav .contact-us.link-contact-us | 0 |  |  | Link Name: linkName=Main Menu: Contact Us; Link Type: linkType=Custom Link;
Global Header: Login Clicks | Event Based Rule | click | .global-header__global-nav .logged-out.login | 0 |  |  | Link Name: linkName=Login; Link Type: linkType=Custom Link;
Global Header: Login to MFS Access | Event Based Rule | click | .global-header__login-container .right_container .login_btn | 0 |  |  | Link Name: linkName=MFS Access Login; Link Type: linkType=Custom Link;
Global Header: Login to MFS.com | Event Based Rule | click | .global-header__login-container .left_container .login_btn | 0 |  |  | Link Name: linkName=MFs.com Login; Link Type: linkType=Custom Link;
Global Header: Logout Clicks | Event Based Rule | click | .global-header__global-nav .logged-in.logout | 0 |  |  | Link Name: linkName=Logout; Link Type: linkType=Custom Link;
Global Header: Logout Clicks | Event Based Rule | click | .global-header__global-nav .logged-in.logout | 0 |  |  | Link Name: linkName=Logout; Link Type: linkType=Custom Link;
Global Header: Main Logo Clicks | Event Based Rule | click | .header .mfs-logo | 0 |  |  | Link Name: linkName=Global Nav Logo; Link Type: linkType=Custom Link;
Global Header: Navigation Link Click | Event Based Rule | click | .global-header__global-nav .sublink-content li.common | 0 |  | function(){var e=$(this).closest(&quot;.js-role-view&quot;).find(&quot;.link-items-label&quot;).text().trim();return _satellite.setVar(&quot;NavigationLinkClick_data_sectionName&quot;,e),_satellite.getVar(&quot;NavigationLinkClick_data_sectionName&quot;),!0} | Link Name: linkName=Main Menu: %NavigationLinkClick_data_sectionName%: %this.@cleanText%; Link Type: linkType=Custom Link;
Global Header: Open Search | Event Based Rule | click | .header .search-logo.js-search-logo | 0 |  |  | Link Name: linkName=Search: Open; Link Type: linkType=Custom Link; Event: event6=event6;
Global Header: Search Filter Applied | Event Based Rule | click | .js-overlay .cta-primary | 0 |  | function(){var e=$(this).hasClass(&quot;js-insights-apply-cta&quot;)?&quot;Insights&quot;:&quot;Products&quot;;_satellite.setVar(&quot;SearchFilterApplied_data_filterType&quot;,e),_satellite.getVar(&quot;SearchFilterApplied_data_filterType&quot;);var t=$(this).closest(&quot;.js-overlay&quot;).find(&quot;input:checked[type='checkbox']&quot;),n=[];return $.each(t,function(e,t){n.push($(t).val())}),_satellite.setVar(&quot;SearchFilterApplied_data_filters&quot;,n.join(&quot;, &quot;)),_satellite.getVar(&quot;SearchFilterApplied_data_filters&quot;),!0} | Link Name: linkName=Filter: %SearchFilterApplied_data_filterType%: %SearchFilterApplied_data_filters%; Link Type: linkType=Custom Link; Event: event24=event24;
Global Header: Search Result Click | Event Based Rule | click | .global-search-result .global-search-tile__product-name | 0 |  | function(){var e=$(&quot;.global-search-result .global-search-tile__product-name&quot;).index(this)+1,t=$(this).closest(&quot;.global-search-tile&quot;).find(&quot;.global-search-tile__type&quot;).text();return t=t.split(&quot;-&quot;)[0].trim(),_satellite.setVar(&quot;GH_SearchResultClick_data_postion&quot;,e),_satellite.getVar(&quot;GH_SearchResultClick_data_postion&quot;),_satellite.setVar(&quot;GH_SearchResultClick_data_section&quot;,t),_satellite.getVar(&quot;GH_SearchResultClick_data_section&quot;),!0} | Link Name: linkName=%GH_SearchResultClick_data_section%: %GH_SearchResultClick_data_postion%; Link Type: linkType=Custom Link;
Global Header: Show More Clicks | Event Based Rule | click | .mega-nav-search__load-more .js-load-more | 0 |  |  | Link Name: linkName=Show More Results; Link Type: linkType=Custom Link;
Global Header: Sort Search Results | Event Based Rule | change | .js-sort-by | 0 |  | function(){var e=$(this).find(&quot;option:selected&quot;).text();return _satellite.setVar(&quot;GH_SortSearchResults_data_sortType&quot;,e),_satellite.getVar(&quot;GH_SortSearchResults_data_sortType&quot;),!0} | Link Name: linkName=Sort: %GH_SortSearchResults_data_sortType%; Link Type: linkType=Custom Link;
Global Header: View All Results Click | Event Based Rule | click | .js-gbl-view-all-btn | 0 |  |  | Link Name: linkName=View All: Overall; Link Type: linkType=Custom Link;
Hamburger Menu Click | Event Based Rule | click | .global-header__hamburger-menu | 0 |  | function(){var e=$(this).hasClass(&quot;is-active&quot;)?&quot;Close Main Menu&quot;:&quot;Expand Main Menu&quot;;return _satellite.setVar(&quot;HamburgerMenuClick_data_action&quot;,e),_satellite.getVar(&quot;HamburgerMenuClick_data_action&quot;),!0} | Link Name: linkName=%HamburgerMenuClick_data_action%; Link Type: linkType=Custom Link; Page URL: pageURL=%PageURL%; Channel: channel=%Channel%; eVar: eVar19=%CampaignUserId%; eVar: eVar2=%Role%; eVar: eVar23=%PageName%; eVar: eVar3=%Location%; eVar: eVar4=%Language%; eVar: eVar5=%LoginStatus%; Prop: prop15=%PageURL%; Prop: prop19=D=v19; Prop: prop2=D=v2; Prop: prop23=D=v23; Prop: prop3=D=v3; Prop: prop4=D=v4; Prop: prop5=D=v5;
Hamburger Menu Location Change | Event Based Rule | click | .global-header__global-nav .change-location .dropdown-with-bg li:not(.region) | 0 |  | function(){var e=_satellite.getVar(&quot;Location&quot;),t=$(this).data(&quot;locationkey&quot;);return _satellite.setVar(&quot;HamburgerMenuLocationChange_data_newloc&quot;,t),_satellite.getVar(&quot;HamburgerMenuLocationChange_data_newloc&quot;),e!=t} | Link Name: linkName=Change Location; Link Type: linkType=Custom Link; Event: event9=event9; Prop: prop13=%Location% to %HamburgerMenuLocationChange_data_newloc%;
Hamburger Menu Role Change | Event Based Rule | click | .global-header__global-nav .role-wrapper .dropdown-with-bg li | 0 |  | function(){var e=_satellite.getVar(&quot;Role&quot;),t=$(this).text();return _satellite.setVar(&quot;HamburgerMenuRoleChange_data_newrole&quot;,t),_satellite.getVar(&quot;HamburgerMenuRoleChange_data_newrole&quot;),e!=t} | Link Name: linkName=Change Role; Link Type: linkType=Custom Link; Event: event8=event8; Prop: prop12=%Role% to %this.@text%;
Hide Login Widget | Event Based Rule | click | .login-register.closed>.login-button | 0 |  |  | Link Name: linkName=Hide Login; Link Type: linkType=Custom Link;
Insights Landing: Author Filters | Event Based Rule | change | .filter-insights__by-author .js-by-author | 0 |  |  | Link Name: linkName=Filter: Author : %this.value%; Link Type: linkType=Custom Link; eVar: eVar19=%CampaignUserId%; eVar: eVar2=%Role%; eVar: eVar23=%PageName%; eVar: eVar3=%Location%; eVar: eVar4=%Language%; eVar: eVar5=%LoginStatus%; Prop: prop15=%PageURL%; Prop: prop19=D=v19; Prop: prop2=D=v2; Prop: prop23=D=v23; Prop: prop3=D=v3; Prop: prop4=D=v4; Prop: prop5=D=v5;
Insights Landing: Checkbox Filter | Event Based Rule | click | .filter-insights__links .js-filter-insights-checkbox | 0 |  | function(){return $(this).is(&quot;:checked&quot;)} | Link Name: linkName=Filter: Checkbox : %this.getAttribute(name)%; Link Type: linkType=Custom Link; eVar: eVar19=%CampaignUserId%; eVar: eVar2=%Role%; eVar: eVar23=%PageName%; eVar: eVar3=%Location%; eVar: eVar4=%Language%; eVar: eVar5=%LoginStatus%; Prop: prop15=%PageURL%; Prop: prop19=D=v19; Prop: prop2=D=v2; Prop: prop23=D=v23; Prop: prop3=D=v3; Prop: prop4=D=v4; Prop: prop5=D=v5;
Insights Landing: Filter Insights Applied | Event Based Rule | click | .js-insights-apply-cta | 0 |  |  | Link Name: linkName=Filter Insights Applied; Link Type: linkType=Custom Link; Event: event21=event21; Channel: channel=%Channel%; eVar: eVar19=%CampaignUserId%; eVar: eVar2=%Role%; eVar: eVar23=%PageName%; eVar: eVar3=%Location%; eVar: eVar4=%Language%; eVar: eVar5=%LoginStatus%; Prop: prop15=%PageURL%; Prop: prop19=D=v19; Prop: prop2=D=v2; Prop: prop23=D=v23; Prop: prop3=D=v3; Prop: prop4=D=v4; Prop: prop5=D=v5;
Insights Landing: Filter Reset | Event Based Rule | click | .filter-insights__bottom-row .js-insights-reset | 0 |  |  | Link Name: linkName=Filter: Reset; Link Type: linkType=Custom Link; eVar: eVar19=%CampaignUserId%; eVar: eVar2=%Role%; eVar: eVar23=%PageName%; eVar: eVar3=%Location%; eVar: eVar4=%Language%; eVar: eVar5=%LoginStatus%; Prop: prop15=%PageURL%; Prop: prop19=D=v19; Prop: prop2=D=v2; Prop: prop23=D=v23; Prop: prop3=D=v3; Prop: prop4=D=v4; Prop: prop5=D=v5;
Insights Landing: Insights Content Clicks | Event Based Rule | click | ul.filter-insights__financial-grid li.js-filter-tile a.js-tile-link | 0 |  | function(){var e=$(&quot;ul.filter-insights__financial-grid li.js-filter-tile a.js-tile-link&quot;).index(this)+1,t=$(this).find(&quot;.js-tile-sub-heading&quot;).text();return _satellite.setVar(&quot;IL_InsightsContentClicks_postion&quot;,e),_satellite.getVar(&quot;IL_InsightsContentClicks_postion&quot;),_satellite.setVar(&quot;IL_InsightsContentClicks_title&quot;,t),_satellite.getVar(&quot;IL_InsightsContentClicks_title&quot;),!0} | Link Name: linkName=Content Click: %IL_InsightsContentClicks_postion%: %IL_InsightsContentClicks_title%; Link Type: linkType=Custom Link; Channel: channel=%Channel%; eVar: eVar19=%CampaignUserId%; eVar: eVar2=%Role%; eVar: eVar23=%PageName%; eVar: eVar3=%Location%; eVar: eVar4=%Language%; eVar: eVar5=%LoginStatus%; Prop: prop15=%PageURL%; Prop: prop19=D=v19; Prop: prop2=D=v2; Prop: prop23=D=v23; Prop: prop3=D=v3; Prop: prop4=D=v4; Prop: prop5=D=v5;
Insights Landing: View Results Below | Event Based Rule | click | .filter-insights__bottom-row .js-insights-apply-cta | 0 |  |  | Link Name: linkName=View Results Below; Link Type: linkType=Custom Link; Channel: channel=%CampaignUserId%; eVar: eVar19=%CampaignUserId%; eVar: eVar2=%Role%; eVar: eVar23=%PageName%; eVar: eVar3=%Location%; eVar: eVar4=%Language%; eVar: eVar5=%LoginStatus%; Prop: prop15=%PageURL%; Prop: prop19=D=v19; Prop: prop2=D=v2; Prop: prop23=D=v23; Prop: prop3=D=v3; Prop: prop4=D=v4; Prop: prop5=D=v5;
Investment Offices | Event Based Rule | click | .mfs-paragraph-heading.legends-1 a | 0 |  | function(){var e=$(this).text();return _satellite.setVar(&quot;GlobalOffice_Legend_name&quot;,e),_satellite.getVar(&quot;GlobalOffice_Legend_name&quot;),!0} | Link Name: linkName=Global: %GlobalOffice_Legend_name%; Link Type: linkType=Custom Link;
Learn More Clicks (TIAA) | Event Based Rule | click | .title-text-cta__time-is-an-asset .cta-primary | 0 |  |  | Link Name: linkName=Time is an Asset: Learn More; Link Type: linkType=Custom Link;
Load More | Event Based Rule | click | .featured-video__grid-area .cta-secondary.show-more | 0 |  |  | Link Name: linkName=Load More: Videos; Link Type: linkType=Custom Link; Event: event27=event27;
Location Click Globe | Event Based Rule | click | .explore-world__globes .explore-world__office-location | 0 |  | function(){var e=$(this).find(&quot;.label&quot;).html();return _satellite.setVar(&quot;GlobeLocation&quot;,e),_satellite.getVar(&quot;GlobeLocation&quot;,e),!0} | Link Name: linkName=Location Click : %GlobeLocation% Map; Link Type: linkType=Custom Link;
Location Click Label | Event Based Rule | click | .js-explore-world .js-link,.office-links-wrapper.in-page-navigation-sticky__navigation .in-page-navigation-sticky__link | 0 |  |  | Link Name: linkName=Location Click : %this.@text%; Link Type: linkType=Custom Link;
Location Map Clicks | Event Based Rule | click | .explore-world__map-icon | 0 |  | function(){var e=$(this).closest(&quot;.js-map-overlay&quot;).data(&quot;loc&quot;);return console.log(&quot;Map clicked : &quot;+e),_satellite.setVar(&quot;LocationMapClicks_data_location&quot;,e),_satellite.getVar(&quot;LocationMapClicks_data_location&quot;),!0} | Link Name: linkName=Map: %LocationMapClicks_data_location%; Link Type: linkType=Custom Link;
Location Return Clicks | Event Based Rule | click | .explore-world__mapOverlay .js-explore-world-cta | 0 |  |  | Link Name: linkName=Return to Locations; Link Type: linkType=Custom Link;
Location Send Clicks | Event Based Rule | click | .js-add-this-link | 0 |  | function(){return _satellite.setVar(&quot;LocationSendClicks_data_location&quot;,$(this).data(&quot;title&quot;)),_satellite.getVar(&quot;LocationSendClicks_data_location&quot;),!0} | Link Name: linkName=Send : %LocationSendClicks_data_location%; Link Type: linkType=Custom Link;
Login Overlay: Login to MFS Access | Event Based Rule | click | .login-register .right_container .login_btn | 0 |  |  | Link Name: linkName=MFS Access Login; Link Type: linkType=Custom Link;
Login Overlay: Login to MFS.com | Event Based Rule | click | .login-register .left_container .login_btn | 0 |  |  | Link Name: linkName=MFS.com Login; Link Type: linkType=Custom Link;
More on this topic | Event Based Rule | click | .vlp-analytics | 0 |  | function(e,t){t=$(this).attr(&quot;data-analytics&quot;);return _satellite.setVar(&quot;moreOnthisTopic&quot;,t),_satellite.getVar(&quot;moreOnthisTopic&quot;),!0} | Link Name: linkName=%moreOnthisTopic%; Link Type: linkType=Custom Link; Event: event26=event26;
Open Section Details | Event Based Rule | click | .nav-main-link-items .link-label | 0 |  | function(){var e=$(this,&quot;.link-items-label&quot;).text().trim();return _satellite.setVar(&quot;OpenSectionDetails_data_sectionName&quot;,e),_satellite.getVar(&quot;OpenSectionDetails_data_sectionName&quot;),!$(this).hasClass(&quot;is-active&quot;)} | Link Name: linkName=Open Section: %OpenSectionDetails_data_sectionName%; Link Type: linkType=Custom Link;
Other Links on the Global Utility Section | Event Based Rule | click | .utility-nav .right-links li a | 0 |  | function(){var e=$(this).text();return _satellite.setVar(&quot;GlobalNavClick_other_links&quot;,e),_satellite.getVar(&quot;GlobalNavClick_other_links&quot;),e} | Link Name: linkName=Global Utility:%GlobalNavClick_other_links%; Link Type: linkType=Custom Link;
Our History | Event Based Rule | click | .our-history .cta-primary | 0 |  |  | Link Name: linkName=About Us: Our History; Link Type: linkType=Custom Link;
PLP: Benchmark Performance Checkbox | Event Based Rule | click | .fund-list-select .benchmark-checkbox__wrapper | 0 |  | function(){return $(this).find(&quot;.js-benchmark-chkbx&quot;).is(&quot;:checked&quot;)} | Link Name: linkName=With Benchmark Performance; Link Type: linkType=Custom Link;
PLP: Checkbox Filters | Event Based Rule | click | .product-fund-finder__link-column .input-wrapper | 0 |  | function(){var e=$(this).text().trim().replace(/\([0-9][0-9]?[0-9]?\)/g,&quot;&quot;).trim();return _satellite.setVar(&quot;PLP_CheckboxFilters_marketingFilter&quot;,e),_satellite.getVar(&quot;PLP_CheckboxFilters_marketingFilter&quot;),!0} | Link Name: linkName=Filter: Check Box : %PLP_CheckboxFilters_marketingFilter%; Link Type: linkType=Custom Link;
PLP: Download Product Results | Event Based Rule | click | .fund-list__characteristics-heading__actionbar .js-exporttoexcel | 0 |  |  | Link Name: linkName=Download %PLP:Product Name%; Link Type: linkType=Custom Link;
PLP: Product Filters Applied | Event Based Rule | click | .fund-list__data-group-list.container input[type=checkbox"]" | 0 |  | function(){var e=$(this).closest(&quot;li&quot;).find(&quot;span&quot;).text().trim();return _satellite.setVar(&quot;PLP_Fund_CharecteristicFilter&quot;,e),_satellite.getVar(&quot;PLP_Fund_CharecteristicFilter&quot;),!0} | Link Name: linkName=Product Filter Applied: %PLP_Fund_CharecteristicFilter%; Link Type: linkType=Custom Link; Event: event22=event22;
PLP: Share Class Filter | Event Based Rule | change | .share-class__list.js-share-class-list | 0 |  |  | Link Name: linkName=Shares Filter; Link Type: linkType=Custom Link;
PLP:Filter Reset | Event Based Rule | click | .product-fund-finder__bottom-row .js-reset-btn | 0 |  |  | Link Name: linkName=Filter: Reset; Link Type: linkType=Custom Link;
Profile: See All Insight | Event Based Rule | click | .profile-insights .js-see-all-insights | 0 |  |  | Link Name: linkName=See All Insights; Link Type: linkType=Custom Link;
Search | Event Based Rule | custom | body | 0 |  |  | Link Name: linkName=%event.detail.type% Search: %event.detail.keyword%; Link Type: linkType=Custom Link; Event: event7=event7; eVar: eVar26=%event.detail.type%; eVar: eVar27=%event.detail.resultCount%; eVar: eVar6=%event.detail.keyword%; Prop: prop26=D=v26; Prop: prop27=D=v27; Prop: prop6=D=v6;
Subhero Clicks - Title | Event Based Rule | click | .insights-callout .content-container__category-title | 0 |  | function(e,t){var n=$(&quot;.insights-callout .content-container__category-title&quot;).index(this)+1;t=$(this).attr(&quot;href&quot;);return _satellite.setVar(&quot;SubheroTileNumber&quot;,n),_satellite.getVar(&quot;SubheroTileNumber&quot;),_satellite.setVar(&quot;SubheroTarget&quot;,t),_satellite.getVar(&quot;SubheroTarget&quot;),!0} | Link Name: linkName=SubHeroClick: %SubheroTileNumber%: %SubheroTarget%: Link Title; Link Type: linkType=Custom Link;
Subhero Clicks - View More | Event Based Rule | click | .insights-callout .cta-primary-text | 0 |  | function(e,t){var n=$(&quot;.insights-callout .cta-primary-text&quot;).index(this)+1;t=$(this).attr(&quot;href&quot;);return _satellite.setVar(&quot;SubheroTileNumber&quot;,n),_satellite.getVar(&quot;SubheroTileNumber&quot;),_satellite.setVar(&quot;SubheroTarget&quot;,t),_satellite.getVar(&quot;SubheroTarget&quot;),null!=$(this).attr(&quot;href&quot;)} | Link Name: linkName=SubHeroClick: %SubheroTileNumber%: %SubheroTarget%: Link View All; Link Type: linkType=Custom Link;
Transcript Click | Event Based Rule | click | .featured-video .video-detail__transcript | 0 |  |  | Link Name: linkName=Read Transcript; Link Type: linkType=Custom Link; Event: event25=event25;
Video Overlay Closed | Event Based Rule | click | #video-lightbox .close-lightbox | 0 |  |  | Link Name: linkName=Video Overlay Closed; Link Type: linkType=Custom Link;
View Event Clicks | Event Based Rule | click | .title-text-cta__events .cta-primary | 0 |  | function(){return _satellite.setVar(&quot;ViewEvent&quot;,&quot;View All Events&quot;),_satellite.getVar(&quot;ViewEvent&quot;),!0} | Link Name: linkName=%ViewEvent%; Link Type: linkType=Custom Link;
Analytics Campaign ID | Page Load Rule | Page Bottom |  | 0
Article: Article ID | Page Load Rule | Page Bottom |  | 0 |  | URI: include .*\/insights\/.* | eVar: eVar1=%ArticleComplianceCode%;
Campaign User Id | Page Load Rule | DOM Ready |  | 0 |  |  | eVar: eVar19=%CampaignUserId%; Prop: prop19=%CampaignUserId%;
Channel | Page Load Rule | DOM Ready |  | 0 |  |  | Channel: channel=%Channel%;
Demandbase Tag | Page Load Rule | Page Bottom |  | 0 |  | URI: include en-us |  |  |  | /*Non-Sequential JavaScript:*/ _satellite.pushAsyncScript(function(event, target, $variables){ (function(d,b,a,s,e){var t=b.createElement(a), fs=b.getElementsByTagName(a)[0];t.async=1;t.id=e;t.src=s; fs.parentNode.insertBefore(t,fs);}) (window,document,&quot;script&quot;,&quot;https://tag.demandbase.com/7c2a8c9f.min.js&quot;,&quot;demandbase_js_lib&quot;); });
DemandbaseAnalytics | Page Load Rule | Page Top |  | 0 |  | URI: include \/en-us\/ |  |  |  | /*Sequential JavaScript:*/ _satellite.pushBlockingScript(function(event, target, $variables){ var callbackscriptdmdbase = document.createElement(&quot;script&quot;); callbackscriptdmdbase.onload = function(){ var apiCalldmdbase = document.createElement(&quot;script&quot;); apiCalldmdbase.type = &quot;text/javascript&quot;; apiCalldmdbase.src = &quot;//api.company-target.com/api/v2/ip.json?key=0579d423e5b570cc3af37312177eab7c&callback=Dmdbase_CDC.callback&quot;; document.head.appendChild(apiCalldmdbase); } callbackscriptdmdbase.type = &quot;text/javascript&quot;; callbackscriptdmdbase.src = &quot;//scripts.demandbase.com/adobeanalytics/7c2a8c9f.min.js&quot;; document.head.appendChild(callbackscriptdmdbase); });
Language | Page Load Rule | DOM Ready |  | 0 |  |  | eVar: eVar4=%Language%; Prop: prop4=%Language%;
Location | Page Load Rule | DOM Ready |  | 0 |  |  | eVar: eVar3=%Location%; Prop: prop3=%Location%;
Logged-in Status | Page Load Rule | Page Bottom |  | 0 |  |  | eVar: eVar5=%LoginStatus%; Prop: prop5=%LoginStatus%;
MFS-social-FB-linkedin | Page Load Rule | Page Top |  | 0 | [5 empty] | <!---Sequential HTML:---> <!-- Facebook Pixel Code --> <script> !function(f,b,e,v,n,t,s) {if(f.fbq)return;n=f.fbq=function(){n.callMethod? n.callMethod.apply(n,arguments):n.queue.push(arguments)}; if(!f._fbq)f._fbq=n;n.push=n;n.loaded=!0;n.version=&quot;2.0&quot;; n.queue=[];t=b.createElement(e);t.async=!0; t.src=v;s=b.getElementsByTagName(e)[0]; s.parentNode.insertBefore(t,s)}(window, document,&quot;script&quot;, &quot;https://connect.facebook.net/en_US/fbevents.js&quot;); fbq(&quot;init&quot;, &quot;538742629854122&quot;); fbq(&quot;track&quot;, &quot;PageView&quot;); </script> <noscript><img height=&quot;1&quot; width=&quot;1&quot; style=&quot;display:none&quot; src=&quot;https://www.facebook.com/tr?id=538742629854122&ev=PageView&noscript=1&quot; /></noscript> <!-- End Facebook Pixel Code --> | <!---Sequential HTML:---> <script type=&quot;text/javascript&quot;> _linkedin_data_partner_id = &quot;367817&quot;; </script><script type=&quot;text/javascript&quot;> (function(){var s = document.getElementsByTagName(&quot;script&quot;)[0]; var b = document.createElement(&quot;script&quot;); b.type = &quot;text/javascript&quot;;b.async = true; b.src = &quot;https://snap.licdn.com/li.lms-analytics/insight.min.js&quot;; s.parentNode.insertBefore(b, s);})(); </script> <noscript> <img height=&quot;1&quot; width=&quot;1&quot; style=&quot;display:none;&quot; alt=&quot;&quot; src=&quot;https://dc.ads.linkedin.com/collect/?pid=367817&fmt=gif&quot; /> </noscript>
MFS-social-twitter | Page Load Rule | Page Bottom |  | 0 | [5 empty] | <!---Sequential HTML:---> <!-- Twitter universal website tag code --> <script> !function(e,t,n,s,u,a){e.twq¦¦(s=e.twq=function(){s.exe?s.exe.apply(s,arguments):s.queue.push(arguments); },s.version=&quot;1.1&quot;,s.queue=[],u=t.createElement(n),u.async=!0,u.src=&quot;//static.ads-twitter.com/uwt.js&quot;, a=t.getElementsByTagName(n)[0],a.parentNode.insertBefore(u,a))}(window,document,&quot;script&quot;); // Insert Twitter Pixel ID and Standard Event data below twq(&quot;init&quot;,&quot;nzmya&quot;); twq(&quot;track&quot;,&quot;PageView&quot;); </script> <!-- End Twitter universal website tag code -->
OLA_2018 1H Brand_529 College Planning Page | Page Load Rule | Page Bottom |  | 0 |  | URI: include en-us/individual-investor/investment-planning/529-college-planning |  |  |  | <!---Sequential HTML:---> <!-- Event snippet for 529 College Planning Page Load on https://www.mfs.com/en-us/individual-investor/investment-planning/529-college-planning.html: Please do not remove. Place this snippet on pages with events you&quot;re tracking. Creation date: 03/05/2018 --> <script> gtag(&quot;event&quot;, &quot;conversion&quot;, { &quot;allow_custom_scripts&quot;: true, &quot;send_to&quot;: &quot;DC-4359444/MFS82-/529co0+standard&quot; }); </script> <noscript> <img src=&quot;https://ad.doubleclick.net/ddm/activity/src=4359444;type=MFS82-;cat=529co0;dc_lat=;dc_rdid=;tag_for_child_directed_treatment=;ord=1?&quot; width=&quot;1&quot; height=&quot;1&quot; alt=&quot;&quot;/> </noscript> <!-- End of event snippet: Please do not remove -->
OLA_2018 1H Brand_All_Global Snippet | Page Load Rule | Page Top |  | 0 | [5 empty] | <!---Sequential HTML:---> <!-- Start of global snippet: Please do not remove Place this snippet between the <head> and </head> tags on every page of your site. --> <!-- Global site tag (gtag.js) - DoubleClick --> <script async src=&quot;https://www.googletagmanager.com/gtag/js?id=DC-4359444&l=GTMdataLayer&quot;></script> <script> window.GTMdataLayer = window.GTMdataLayer ¦¦ []; function gtag(){GTMdataLayer.push(arguments);} gtag(&quot;js&quot;, new Date()); gtag(&quot;config&quot;, &quot;DC-4359444&quot;); </script> <!-- End of global snippet: Please do not remove -->
OLA_2018 1H Brand_Asset Allocation Strategies | Page Load Rule | Page Bottom |  | 0 |  | URI: include en-us/individual-investor/product-strategies/asset-allocation-strategies |  |  |  | <!---Sequential HTML:---> <!-- Event snippet for Asset Allocation Strategies Page Load on https://www.mfs.com/en-us/individual-investor/product-strategies/asset-allocation-strategies.html: Please do not remove. Place this snippet on pages with events you&quot;re tracking. Creation date: 03/05/2018 --> <script> gtag(&quot;event&quot;, &quot;conversion&quot;, { &quot;allow_custom_scripts&quot;: true, &quot;send_to&quot;: &quot;DC-4359444/MFS82-/asset0+standard&quot; }); </script> <noscript> <img src=&quot;https://ad.doubleclick.net/ddm/activity/src=4359444;type=MFS82-;cat=asset0;dc_lat=;dc_rdid=;tag_for_child_directed_treatment=;ord=1?&quot; width=&quot;1&quot; height=&quot;1&quot; alt=&quot;&quot;/> </noscript> <!-- End of event snippet: Please do not remove -->
OLA_2018 1H Brand_Closed End Funds | Page Load Rule | Page Bottom |  | 0 |  | URI: include en-us/individual-investor/product-strategies/closed-end-funds |  |  |  | <!---Sequential HTML:---> <!-- Event snippet for Closed End Funds Page Load on https://www.mfs.com/en-us/individual-investor/product-strategies/closed-end-funds.html: Please do not remove. Place this snippet on pages with events you&quot;re tracking. Creation date: 03/05/2018 --> <script> gtag(&quot;event&quot;, &quot;conversion&quot;, { &quot;allow_custom_scripts&quot;: true, &quot;send_to&quot;: &quot;DC-4359444/MFS82-/close0+standard&quot; }); </script> <noscript> <img src=&quot;https://ad.doubleclick.net/ddm/activity/src=4359444;type=MFS82-;cat=close0;dc_lat=;dc_rdid=;tag_for_child_directed_treatment=;ord=1?&quot; width=&quot;1&quot; height=&quot;1&quot; alt=&quot;&quot;/> </noscript> <!-- End of event snippet: Please do not remove -->
OLA_2018 1H Brand_Contact US | Page Load Rule | Page Bottom |  | 0 |  | URI: include en-us/individual-investor/contact-us |  |  |  | <!---Sequential HTML:---> <!-- Event snippet for Contact Us Page Load on https://www.mfs.com/en-us/individual-investor/contact-us.html: Please do not remove. Place this snippet on pages with events you&quot;re tracking. Creation date: 03/05/2018 --> <script> gtag(&quot;event&quot;, &quot;conversion&quot;, { &quot;allow_custom_scripts&quot;: true, &quot;send_to&quot;: &quot;DC-4359444/MFS82-/conta000+standard&quot; }); </script> <noscript> <img src=&quot;https://ad.doubleclick.net/ddm/activity/src=4359444;type=MFS82-;cat=conta000;dc_lat=;dc_rdid=;tag_for_child_directed_treatment=;ord=1?&quot; width=&quot;1&quot; height=&quot;1&quot; alt=&quot;&quot;/> </noscript> <!-- End of event snippet: Please do not remove -->
OLA_2018 1H Brand_Fund Ratings | Page Load Rule | Page Bottom |  | 0 |  | URI: include en-us/individual-investor/product-strategies/fund-ratings |  |  |  | <!---Sequential HTML:---> <!-- Event snippet for Fund Ratings Page Load on https://www.mfs.com/en-us/individual-investor/product-strategies/fund-ratings.html: Please do not remove. Place this snippet on pages with events you&quot;re tracking. Creation date: 03/05/2018 --> <script> gtag(&quot;event&quot;, &quot;conversion&quot;, { &quot;allow_custom_scripts&quot;: true, &quot;send_to&quot;: &quot;DC-4359444/MFS82-/fundr0+standard&quot; }); </script> <noscript> <img src=&quot;https://ad.doubleclick.net/ddm/activity/src=4359444;type=MFS82-;cat=fundr0;dc_lat=;dc_rdid=;tag_for_child_directed_treatment=;ord=1?&quot; width=&quot;1&quot; height=&quot;1&quot; alt=&quot;&quot;/> </noscript> <!-- End of event snippet: Please do not remove -->
OLA_2018 1H Brand_Home Page | Page Load Rule | Page Bottom |  | 0 |  | URI: include www.mfs.com\/en-us$¦\/$ |  |  |  | <!---Sequential HTML:---> <!-- Event snippet for Home Page Page Load on https://www.mfs.com/en-us/: Please do not remove. Place this snippet on pages with events you&quot;re tracking. Creation date: 03/05/2018 --> <script> gtag(&quot;event&quot;, &quot;conversion&quot;, { &quot;allow_custom_scripts&quot;: true, &quot;send_to&quot;: &quot;DC-4359444/MFS82-/homep0+standard&quot; }); </script> <noscript> <img src=&quot;https://ad.doubleclick.net/ddm/activity/src=4359444;type=MFS82-;cat=homep0;dc_lat=;dc_rdid=;tag_for_child_directed_treatment=;ord=1?&quot; width=&quot;1&quot; height=&quot;1&quot; alt=&quot;&quot;/> </noscript> <!-- End of event snippet: Please do not remove -->
OLA_2018 1H Brand_Individual Investor Homepage | Page Load Rule | Page Bottom |  | 0 |  | URI: include \/en-us\/individual-investor.html |  |  |  | <!---Sequential HTML:---> <!-- Event snippet for Individual Investor Homepage Page Load on https://www.mfs.com/en-us/individual-investor.html: Please do not remove. Place this snippet on pages with events you&quot;re tracking. Creation date: 03/05/2018 --> <script> gtag(&quot;event&quot;, &quot;conversion&quot;, { &quot;allow_custom_scripts&quot;: true, &quot;send_to&quot;: &quot;DC-4359444/MFS82-/indiv0+standard&quot; }); </script> <noscript> <img src=&quot;https://ad.doubleclick.net/ddm/activity/src=4359444;type=MFS82-;cat=indiv0;dc_lat=;dc_rdid=;tag_for_child_directed_treatment=;ord=1?&quot; width=&quot;1&quot; height=&quot;1&quot; alt=&quot;&quot;/> </noscript> <!-- End of event snippet: Please do not remove -->
OLA_2018 1H Brand_Mutual Funds | Page Load Rule | Page Bottom |  | 0 |  | URI: include en-us/individual-investor/product-strategies/mutual-funds |  |  |  | <!---Sequential HTML:---> <!-- Event snippet for Mutual Funds Page Load on https://www.mfs.com/en-us/individual-investor/product-strategies/mutual-funds.html: Please do not remove. Place this snippet on pages with events you&quot;re tracking. Creation date: 03/05/2018 --> <script> gtag(&quot;event&quot;, &quot;conversion&quot;, { &quot;allow_custom_scripts&quot;: true, &quot;send_to&quot;: &quot;DC-4359444/MFS82-/mutua0+standard&quot; }); </script> <noscript> <img src=&quot;https://ad.doubleclick.net/ddm/activity/src=4359444;type=MFS82-;cat=mutua0;dc_lat=;dc_rdid=;tag_for_child_directed_treatment=;ord=1?&quot; width=&quot;1&quot; height=&quot;1&quot; alt=&quot;&quot;/> </noscript> <!-- End of event snippet: Please do not remove -->
OLA_2018 1H Brand_Register | Page Load Rule | Page Bottom |  | 0 |  | URI: include en-us/register.html |  |  |  | <!---Sequential HTML:---> <!-- Event snippet for Register Page Load on https://www.mfs.com/en-us/register.html: Please do not remove. Place this snippet on pages with events you&quot;re tracking. Creation date: 03/05/2018 --> <script> gtag(&quot;event&quot;, &quot;conversion&quot;, { &quot;allow_custom_scripts&quot;: true, &quot;send_to&quot;: &quot;DC-4359444/MFS82-/regis0+standard&quot; }); </script> <noscript> <img src=&quot;https://ad.doubleclick.net/ddm/activity/src=4359444;type=MFS82-;cat=regis0;dc_lat=;dc_rdid=;tag_for_child_directed_treatment=;ord=1?&quot; width=&quot;1&quot; height=&quot;1&quot; alt=&quot;&quot;/> </noscript> <!-- End of event snippet: Please do not remove -->
OLA_2018 1H Brand_Retirement Planning | Page Load Rule | Page Bottom |  | 0 |  | URI: include en-us/individual-investor/investment-planning/retirement-planning |  |  |  | <!---Sequential HTML:---> <!-- Event snippet for Retirement Planning Page Load on https://www.mfs.com/en-us/individual-investor/investment-planning/retirement-planning.html: Please do not remove. Place this snippet on pages with events you&quot;re tracking. Creation date: 03/05/2018 --> <script> gtag(&quot;event&quot;, &quot;conversion&quot;, { &quot;allow_custom_scripts&quot;: true, &quot;send_to&quot;: &quot;DC-4359444/MFS82-/retir000+standard&quot; }); </script> <noscript> <img src=&quot;https://ad.doubleclick.net/ddm/activity/src=4359444;type=MFS82-;cat=retir000;dc_lat=;dc_rdid=;tag_for_child_directed_treatment=;ord=1?&quot; width=&quot;1&quot; height=&quot;1&quot; alt=&quot;&quot;/> </noscript> <!-- End of event snippet: Please do not remove -->
OLA_2018 1H Brand_Separately Managed Accounts | Page Load Rule | Page Bottom |  | 0 |  | URI: include en-us/individual-investor/product-strategies/separately-managed-accounts |  |  |  | <!---Sequential HTML:---> <!-- Event snippet for Separately Managed Accounts Page Load on https://www.mfs.com/en-us/individual-investor/product-strategies/separately-managed-accounts.html: Please do not remove. Place this snippet on pages with events you&quot;re tracking. Creation date: 03/05/2018 --> <script> gtag(&quot;event&quot;, &quot;conversion&quot;, { &quot;allow_custom_scripts&quot;: true, &quot;send_to&quot;: &quot;DC-4359444/MFS82-/separ0+standard&quot; }); </script> <noscript> <img src=&quot;https://ad.doubleclick.net/ddm/activity/src=4359444;type=MFS82-;cat=separ0;dc_lat=;dc_rdid=;tag_for_child_directed_treatment=;ord=1?&quot; width=&quot;1&quot; height=&quot;1&quot; alt=&quot;&quot;/> </noscript> <!-- End of event snippet: Please do not remove -->
OLA_2018 1H Brand_VI Portfolios | Page Load Rule | Page Bottom |  | 0 |  | URI: include variable-insurance-portfolios |  |  |  | <!---Sequential HTML:---> <!-- Event snippet for Variable Insurance Portfolios Page Load on https://www.mfs.com/en-us/individual-investor/product-strategies/variable-insurance-portfolios.html: Please do not remove. Place this snippet on pages with events you&quot;re tracking. Creation date: 03/05/2018 --> <script> gtag(&quot;event&quot;, &quot;conversion&quot;, { &quot;allow_custom_scripts&quot;: true, &quot;send_to&quot;: &quot;DC-4359444/MFS82-/varia0+standard&quot; }); </script> <noscript> <img src=&quot;https://ad.doubleclick.net/ddm/activity/src=4359444;type=MFS82-;cat=varia0;dc_lat=;dc_rdid=;tag_for_child_directed_treatment=;ord=1?&quot; width=&quot;1&quot; height=&quot;1&quot; alt=&quot;&quot;/> </noscript> <!-- End of event snippet: Please do not remove -->
OLA_2018 1H Brand_What We Do FI | Page Load Rule | Page Bottom |  | 0 |  | URI: include what-we-do/fixed-income |  |  |  | <!---Sequential HTML:---> <!-- Event snippet for Fixed Income Page Load on https://www.mfs.com/en-us/what-we-do/fixed-income.html: Please do not remove. Place this snippet on pages with events you&quot;re tracking. Creation date: 03/13/2018 --> <script> gtag(&quot;event&quot;, &quot;conversion&quot;, { &quot;allow_custom_scripts&quot;: true, &quot;send_to&quot;: &quot;DC-4359444/MFS82-/fixed008+standard&quot; }); </script> <noscript><img src=&quot;https://ad.doubleclick.net/ddm/activity/src=4359444;type=MFS82-;cat=fixed008;dc_lat=;dc_rdid=;tag_for_child_directed_treatment=;ord=1?&quot; width=&quot;1&quot; height=&quot;1&quot; alt=&quot;&quot;/></noscript> <!-- End of event snippet: Please do not remove -->
OLA_2018 1H Brand_What We Do Overview Page | Page Load Rule | Page Bottom |  | 0 |  | URI: include \/en-us/what-we-do.html |  |  |  | <!---Sequential HTML:---> <!-- Event snippet for What We Do Overview Page Load on https://www.mfs.com/en-us/what-we-do.html: Please do not remove. Place this snippet on pages with events you&quot;re tracking. Creation date: 03/05/2018 --> <script> gtag(&quot;event&quot;, &quot;conversion&quot;, { &quot;allow_custom_scripts&quot;: true, &quot;send_to&quot;: &quot;DC-4359444/MFS82-/whatw010+standard&quot; }); </script> <noscript> <img src=&quot;https://ad.doubleclick.net/ddm/activity/src=4359444;type=MFS82-;cat=whatw010;dc_lat=;dc_rdid=;tag_for_child_directed_treatment=;ord=1?&quot; width=&quot;1&quot; height=&quot;1&quot; alt=&quot;&quot;/> </noscript> <!-- End of event snippet: Please do not remove -->
OLA_2018 1H Brand_Who We Are Overview | Page Load Rule | Page Bottom |  | 0 |  | URI: include en-us/who-we-are |  |  |  | <!---Sequential HTML:---> <!-- Event snippet for Who We Are Overview Page Load on https://www.mfs.com/en-us/who-we-are.html: Please do not remove. Place this snippet on pages with events you&quot;re tracking. Creation date: 03/05/2018 --> <script> gtag(&quot;event&quot;, &quot;conversion&quot;, { &quot;allow_custom_scripts&quot;: true, &quot;send_to&quot;: &quot;DC-4359444/MFS82-/whowe0+standard&quot; }); </script> <noscript> <img src=&quot;https://ad.doubleclick.net/ddm/activity/src=4359444;type=MFS82-;cat=whowe0;dc_lat=;dc_rdid=;tag_for_child_directed_treatment=;ord=1?&quot; width=&quot;1&quot; height=&quot;1&quot; alt=&quot;&quot;/> </noscript> <!-- End of event snippet: Please do not remove -->
OLA_2018 FI Brand_Insights | Page Load Rule | Page Bottom |  | 0 |  | URI: include en-us/insights |  |  |  | <!---Sequential HTML:---> <!-- Event snippet for Insights Page Load on https://www.mfs.com/en-us/insights.html: Please do not remove. Place this snippet on pages with events you&quot;re tracking. Creation date: 03/05/2018 --> <script> gtag(&quot;event&quot;, &quot;conversion&quot;, { &quot;allow_custom_scripts&quot;: true, &quot;send_to&quot;: &quot;DC-4359444/MFS82-/insig003+standard&quot; }); </script> <noscript> <img src=&quot;https://ad.doubleclick.net/ddm/activity/src=4359444;type=MFS82-;cat=insig003;dc_lat=;dc_rdid=;tag_for_child_directed_treatment=;ord=1?&quot; width=&quot;1&quot; height=&quot;1&quot; alt=&quot;&quot;/> </noscript> <!-- End of event snippet: Please do not remove -->
PLP: Horizontal Scroll | Page Load Rule | Page Bottom |  | 0 | [5 empty] | /*Non-Sequential JavaScript:*/ _satellite.pushAsyncScript(function(event, target, $variables){ // will report scroll first time and every 2 seconds thereoff var timeout = 2 * 1000 // timeout after which another scroll event is reported $(&quot;.hscroll.js-fund-list-scroll&quot;).scroll(function(evt){ //console.log(&quot;scoll&quot;); var lastScrollTime = parseFloat(_satellite.getVar(&quot;PLP_HorozontalScroll_lastScrollTime&quot;)); var report = false; var now = (new Date()).getTime(); if ( !isNaN(lastScrollTime)) { var diff = (now - lastScrollTime); report = diff > timeout ? true : false; } else { // first time report = true; } if (report) { _satellite.setVar(&quot;PLP_HorozontalScroll_lastScrollTime&quot;, now); s.tl(this,&quot;o&quot;, &quot;Horozontal Scroll&quot;); } }); });
PLP: Performance Tool - Pricing Distribution (Desktop) | Page Load Rule | Page Bottom |  | 0 |  | function(){return $(&quot;#stock-cnt&quot;).length>0} |  |  |  | /*Sequential JavaScript:*/ _satellite.pushBlockingScript(function(event, target, $variables){ (function (H) { var lastReportTime; H.wrap(H.Chart.prototype, &quot;redraw&quot;, function (proceed, points) { // proceed as usual... proceed.apply(this, Array.prototype.slice.call(arguments, 1)); // now execute custom logic - here we will do analytics tracking var now = new Date().getTime(); var diff = lastReportTime == null ? 5000 : now - lastReportTime; // again report usage if still using after 1.5 sec if (diff > 1500 ) { //console.log(&quot;will track this as Performance Tool Usage...&quot;); lastReportTime = now; _satellite.track(&quot;performance_tool_usage&quot;); } }); }(Highcharts)); });
Page Name | Page Load Rule | DOM Ready |  | 0 |  |  | eVar: eVar23=%PageName%; Prop: prop23=%PageName%;
Page Title | Page Load Rule | Page Bottom |  | 0 |  |  | eVar: eVar30=%PageTitle%; Prop: prop30=D=v30;
Page URL | Page Load Rule | DOM Ready |  | 0 |  |  | Prop: prop15=%PageURL%;
Placeholder | Page Load Rule | Page Bottom |  | 0 | [5 empty] | <!---Sequential HTML:---> <style type=&quot;text/css&quot;> .in-page-navigation--bg-maroon .transcript-label { background: transparent; color: #fff; } /* Fix for IE flyout */ body.IE.search-flyout .title-text-cta__time-is-an-asset .content-container{ width:auto; } </style> | /*Sequential JavaScript:*/ _satellite.pushBlockingScript(function(event, target, $variables){ var bubbleText = $(&quot;.mobile .bubble-maroon .bubble__text&quot;); if (bubbleText != null && bubbleText.length > 0) { bubbleText.html(bubbleText.html().replace(&quot;Video Dolor Consecteteur&quot;, &quot;Watch Video&quot;)); } });
Placeholder ¦ Hide Performance Results in VIT | Page Load Rule | Page Bottom |  | 0 |  | URI: include \/variable-insurance-portfolios,\/variable-insurance-portfolios-ii.,\/variable-insurance-portfolios-iii |  |  |  | <!---Sequential HTML:---> <style> .variable-insurance-portfolios-ii .performace-summary__list.js-select-performance-summary { display:none; } .variable-insurance-portfolios .performace-summary__list.js-select-performance-summary { display:none; } .variable-insurance-portfolios-iii .performace-summary__list.js-select-performance-summary { display:none; } </style>
Placeholder: Events Landing | Page Load Rule | DOM Ready |  | 0 |  | URI: include \/events.html |  |  |  | /*Non-Sequential JavaScript:*/ _satellite.pushAsyncScript(function(event, target, $variables){ var mobileImg = $(&quot;.event-detail__hero-image picture img&quot;); var imgSet = $(&quot;.event-detail__hero-image picture source&quot;).attr(&quot;srcset&quot;); var newImg = imgSet.replace(&quot;.jpg/jcr:content&quot;, &quot;_article_750x400.jpg/jcr:content&quot;); console.log(&quot;MOBILE IMG: &quot; + mobileImg); console.log(&quot;IMGSET : &quot; + imgSet); console.log(&quot;NEWIMG : &quot; + newImg); function replaceImg() { if ($(mobileImg).attr(&quot;src&quot;) != newImg) { $(&quot;.event-detail__hero-image picture source&quot;).attr(&quot;srcset&quot;,newImg); $(mobileImg).attr(&quot;src&quot;, newImg); } } var imgTimer = setInterval(function(){ replaceImg(); }, 100); $(window).load(function(){ replaceImg(); }); });
Placeholder: Insights Landing | Page Load Rule | Page Bottom |  | 0 |  | URI: include insights.html |  |  |  | /*Sequential JavaScript:*/ _satellite.pushBlockingScript(function(event, target, $variables){ var mobileImg = &quot;/content/dam/mfs-enterprise/mfscom/images/objects/us/mobile-gradient-background.jpg&quot;; function replaceImg() { $($(&quot;.insight-landing__col-6 picture source&quot;)[0]).attr(&quot;srcset&quot;,mobileImg) var currWidth = $(window).width(); if (currWidth < 1023) { $(&quot;.insight-landing__col-6 picture img&quot;).attr(&quot;src&quot;,mobileImg); } } var imgTimer = setInterval(function(){ replaceImg(); }, 100); $(window).load(function(){ replaceImg(); }); });
Placeholder: Prudent Investor Fund Summary | Page Load Rule | Page Bottom |  | 0 |  | URI: include mfs-prudent-investor-fund |  |  |  | /*Sequential JavaScript:*/ _satellite.pushBlockingScript(function(event, target, $variables){ $(&quot;.rich-text.rich-text__articleSummary&quot;).append(&quot;<p>May use cash, derivatives, and fixed income instruments to manage market exposure and downside risk.</p>&quot;); });
Placeholder:ManagedWealth fund- Fund Position | Page Load Rule | Page Bottom |  | 0 |  | URI: include managed-wealth-fund |  |  |  | /*Sequential JavaScript:*/ _satellite.pushBlockingScript(function(event, target, $variables){ $(&quot;tr[data-type^=&quot;SUB&quot;]&quot;).each( function(k,v){ var rowHead = $(&quot;td:nth-of-type(1)&quot;,v).text().trim(); if (rowHead === &quot;Strategic Allocation&quot; ¦¦ rowHead === &quot;Market Exposure Overlay&quot;) { $(&quot;td:nth-of-type(3)&quot;,v).text(&quot;&quot;); $(&quot;td:nth-of-type(4)&quot;,v).text(&quot;&quot;); } }); });
Placeholder_MFIWX_R6_Launch | Page Load Rule | Page Bottom |  | 0 |  | URI: include product-strategies/mutual-funds/MFIWX-mfs-strategic-income-fund-share-R6.html |  |  |  | /*Sequential JavaScript:*/ _satellite.pushBlockingScript(function(event, target, $variables){ $(&quot;.product-detail__performance-tab-column-chart-subheading&quot;).html(&quot;<p>No data is currently available.</p>&quot;); $(&quot;.product-detail__performance-tab-table.averageROR&quot;).html(&quot;<p>No data is currently available.</p>&quot;); });
Profile : Bio Name | Page Load Rule | Page Bottom |  | 0 |  | function(){var e=$(&quot;.profile-banner .profile-banner__name&quot;).find(&quot;h1&quot;).text();return e.length>0&&(_satellite.setVar(&quot;Profile_bioName&quot;,e),_satellite.getVar(&quot;Profile_bioName&quot;)),e.length>0}
Role | Page Load Rule | DOM Ready |  | 0 |  |  | eVar: eVar2=%Role%; Prop: prop2=%Role%;
performance_tool_usage | Direct Call Rule | _satellite.track("performance_tool_usage") |  | 0 |  |  | Link Name: linkName=Performance Tool Usage; Link Type: linkType=Custom Link; Event: event23=event23;
video_loaded | Direct Call Rule | _satellite.track("video_loaded") |  | 0 | [5 empty] | /*Non-Sequential JavaScript:*/ _satellite.pushAsyncScript(function(event, target, $variables){ /* * Custom Code: Video Analytics using pure Brightcove API. * Adobe Analytics Media Module is old, Heartbeat requires account level configuration. */ try { _satellite.notify(&quot;APP.DTM.videoLoaded started.&quot;); // unsetting the videojs variable, so that videojs = undefined; // wait for BC API to load. var bcLoaded = $.Deferred(); $.when(bcLoaded).then(function () { if (videojs.length > 0) { var mediaPlayerName = &quot;Brightcove Player&quot;; //Required hard code player name here. //var player = videojs(&quot;myExperience_html5_api&quot;); videojs(&quot;myExperience_html5_api&quot;).ready(function () { var player = this; var mediainfo, lastPercentViewSent; mediainfo = player.mediainfo; // custom variables to be sent for all events s.eVar24 = s.prop24 = mediainfo.name; s.eVar25 = s.prop25 = mediainfo.id; s.eVar17 = s.prop17 = mediainfo.name + &quot;(&quot; + mediainfo.id + &quot;)&quot;; s.eVar28 = s.prop28 = Math.round(mediainfo.duration); player.on(&quot;loadstart&quot;, function () { _satellite.notify(&quot;player id = &quot; + player); _satellite.notify(&quot;video js= &quot; + videojs(&quot;myExperience_html5_api&quot;)); _satellite.notify(&quot;mediainfo&quot;, player.mediainfo); mediainfo = player.mediainfo; // custom variables to be sent for all events s.eVar24 = s.prop24 = mediainfo.name; s.eVar25 = s.prop25 = mediainfo.id; s.eVar17 = s.prop17 = mediainfo.name + &quot;(&quot; + mediainfo.id + &quot;)&quot;; s.eVar28 = s.prop28 = Math.round(mediainfo.duration); }); player.on(&quot;play&quot;, function (e) { console.log(&quot;player play&quot;); // reinitialize media info (used for replays) mediainfo = player.mediainfo; // custom variables to be sent for all events s.eVar24 = s.prop24 = mediainfo.name; s.eVar25 = s.prop25 = mediainfo.id; s.eVar17 = s.prop17 = mediainfo.name + &quot;(&quot; + mediainfo.id + &quot;)&quot;; s.eVar28 = s.prop28 = Math.round(mediainfo.duration); s.events = &quot;event14&quot;; // handle video resume s.tl(player, &quot;o&quot;, &quot;Video Play&quot;); }); player.on(&quot;pause&quot;, function (e) { console.log(&quot;player pause&quot;); var mediaOffset = Math.floor(player.currentTime()); //Required video position var timeToEnd = mediainfo.duration - mediaOffset; _satellite.notify(&quot;Media Offset: &quot; + mediaOffset); _satellite.notify(&quot;Media Time to End: &quot; + timeToEnd); if (timeToEnd < 1) { s.events = &quot;event19&quot;; // consider video as complete s.tl(player, &quot;o&quot;, &quot;Video Complete&quot;); } else { //s.Media.stop(mediainfo.name,mediaOffset); s.events = &quot;event20&quot;; s.tl(player, &quot;o&quot;, &quot;Video Paused&quot;); } }); player.on(&quot;timeupdate&quot;, function (e) { var mediaOffset = Math.floor(player.currentTime()); //Required video position //console.log(&quot;player timeupdate &quot; + mediaOffset); if ( mediainfo.duration ) { var totalDuration = mediainfo.duration; // where are we? var percentageViewed = Math.ceil((mediaOffset / totalDuration) * 100); if ((percentageViewed == 25 ¦¦ percentageViewed == 50 ¦¦ percentageViewed == 75) && percentageViewed != lastPercentViewSent) { switch (percentageViewed) { case 25: s.events = &quot;event16&quot;; lastPercentViewSent = percentageViewed; break; case 50: s.events = &quot;event17&quot;; lastPercentViewSent = percentageViewed; break; case 75: s.events = &quot;event18&quot;; lastPercentViewSent = percentageViewed; break; } s.tl(player, &quot;o&quot;, &quot;Video &quot; + percentageViewed + &quot;% Viewed &quot;); } } }); }); } else { console.warn(&quot;Brightcove API not loaded... cannot track video&quot;); } }); // now wait for BC API to load function checkBCLoaded() { if (typeof videojs !== &quot;undefined&quot;) { try { if ( typeof videojs(&quot;myExperience_html5_api&quot;) != &quot;undefined&quot; && typeof videojs(&quot;myExperience_html5_api&quot;).mediainfo != &quot;undefined&quot;) { bcLoaded.resolve(); } } catch(ex) { // still waiting for video player to be loaded setTimeout(checkBCLoaded, 100); } } else { setTimeout(checkBCLoaded, 100); } } checkBCLoaded(); } catch (e) { console.error(&quot;Could not track video!&quot;, e); } });
Channel | Page Load Rule | DOM Ready |  | 0 |  |  | Channel: channel=%Channel%;
Language | Page Load Rule | DOM Ready |  | 0 |  |  | eVar: eVar4=%Language%; Prop: prop4=%Language%;
Location | Page Load Rule | DOM Ready |  | 0 |  |  | eVar: eVar3=%Location%; Prop: prop3=%Location%;
Role | Page Load Rule | DOM Ready |  | 0 |  |  | eVar: eVar2=%Role%; Prop: prop2=%Role%;
Data Elements
Name | Type | Details | Scope | Status | Default Value
ArticleComplianceCode | Custom JavaScript | /*Custom JavaScript:*/ function(){var e=$(&quot;.article-page__content-grid .col-md-9.right-section&quot;).text().trim(),t=e.length,n=e.substr(t-150).match(/[0-9]{5}\.[0-9][0-9]?/g);return null!=n&&n.length>0?n[0]:&quot;&quot;} | pageview | 3
campaignID | Custom JavaScript | /*Custom JavaScript:*/ function(){ var e=_satellite.getQueryParam(&quot;utm_source&quot;),t=_satellite.getQueryParam(&quot;utm_medium&quot;),i=_satellite.getQueryParam(&quot;utm_term&quot;),a=_satellite.getQueryParam(&quot;utm_campaign&quot;),r=_satellite.getQueryParam(&quot;utm_content&quot;);return e?e+&quot;:&quot;+t+&quot;:&quot;+i+&quot;:&quot;+a+&quot;:&quot;+r:n} | pageview | 3
CampaignUserId | Query Parameter | cid | pageview | 3
Channel | Custom JavaScript | /*Custom JavaScript:*/ function(){var e=&quot;&quot;,n=t.head.querySelector(&quot;meta[name=sitesection]&quot;);if(null!=n&&(e=n.content),0==e.length){var i=$(&quot;#analytics-page-name&quot;).attr(&quot;content&quot;);if(void 0!==i){var a=i.split(&quot;:&quot;);1==a.length?e=a[0]:a.length>1&&(e=a[1])}}return _satellite.notify(&quot;Channel ~> &quot;+e),e} | pageview | 3
Language | Custom JavaScript | /*Custom JavaScript:*/ function(){APP&&APP.global&&null==APP.global.user&&APP.global.init();var e=APP.global.user.locale();return null!=e?e:$(&quot;meta[name=language]&quot;).attr(&quot;content&quot;)} | pageview | 3
Location | Custom JavaScript | /*Custom JavaScript:*/ function(){return APP&&APP.global&&null==APP.global.user&&APP.global.init(),console.log(&quot;location rule of analytics&quot;,APP.global.user.location(&quot;cookie&quot;)),APP.global.user.location(&quot;cookie&quot;)} | pageview | 3 | us
LoginStatus | Custom JavaScript | /*Custom JavaScript:*/ function(){return APP.global.user.loggedIn()?&quot;Logged In&quot;:&quot;Logged Out&quot;} | pageview | 3
PageName | Custom JavaScript | /*Custom JavaScript:*/ function(){var e=&quot;en&quot;,n=$(&quot;sitesection&quot;).attr(&quot;content&quot;),i=$(&quot;#analytics-page-name&quot;).attr(&quot;content&quot;);if(i.length>0&&i.split(&quot;:&quot;).length>1){var a=i.split(&quot;:&quot;);i=i.replace(a[0]+&quot;:&quot;,&quot;&quot;)}var r=t.location.pathname.split(&quot;/&quot;);/^[a-z][a-z](\-[a-z][a-z])?$/.test(r[1])&&(e=r[1]),null!=e&&0!=e.length¦¦(e=APP.global.user.locale(&quot;cookie&quot;).replace(&quot;_&quot;,&quot;-&quot;));var o=r[r.length-1].split(&quot;.html&quot;)[0],s=(null!=n?&quot;:&quot;+n:&quot;&quot;)+&quot;:&quot;+(null!=o&&o.length>0?o:&quot;home&quot;);return e+(null!=i?&quot;:&quot;+i:s)} | pageview | 3 | PAGE NAME NOT DEFINED
PageTitle | JavaScript Variable | document.title | pageview | 3
PageURL | Custom JavaScript | /*Custom JavaScript:*/ function(){return t.location.origin+t.location.pathname} | pageview | 3
PLP:Product Name | Custom JavaScript | /*Custom JavaScript:*/ function(){return $(&quot;.desktop .product-fund-finder__title&quot;).text().trim()} | pageview | 3
Product Finder Investment Option | Custom JavaScript | /*Custom JavaScript:*/ function(){return $(this).find(&quot;select option:selected&quot;).text()} | pageview | 3
Role | Custom JavaScript | /*Custom JavaScript:*/ function(){var e={inv:&quot;Individual Investor&quot;,iprof_us:&quot;Investment Professional&quot;,iprof_it:&quot;Investment Professional&quot;,insti:&quot;Institutions & Consultants&quot;,analyst:&quot;Research Analyst&quot;,iprof:&quot;Financial Advisor&quot;};APP&&APP.global&&null==APP.global.user&&APP.global.init();var t=APP.global.user.role(&quot;cookies&quot;),n=e[t+&quot;_&quot;+APP.global.user.location(&quot;cookie&quot;)];return null==n?e[t]:n} | pageview | 3
utm_campaign | Query Parameter | utm_campaign | pageview | 3
utm_content | Query Parameter | utm_content | pageview | 3
utm_medium | Query Parameter | utm_medium | pageview | 3
utm_source | Query Parameter | utm_source | pageview | 3
utm_term | Query Parameter | utm_term | pageview | 3